## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone 1: Preparation for Tablet Integration
Conduct staff meetings to prepare for tablet integration | Workflow, strategies, features, concerns, recommendations | 1 | 2 hours | 5-7 hours | 2 days | H
Brainstorm on various ways to track project effeciency |  | 1 | 2 hours | 5-7 hours | 2 days | H
Develop a process to record and analyze new metrics |  | 1.5 | 4 hours | 1 day | 2 days | H
Research different tablets and their features |  | 4 | 2 days | 3 days | 5 days | H
Research 2 to 3 vendors |  | 3 | 1 day | 2 days | 5 days | H
Milestone 2: Purchasing of Tablets
Determine tablets and review costs |  | 5 | 3 days | 5 days | 7 days | M
Test out different tablets | Review options | 3 | 1 day | 2 days | 4 days | M
Choose a suitable tablet |  | 1 | 1 day | 1 day | 2 days | M
Create contracts, purchase orders, and statements of work for vendors |  | 5 | 2 days | 4 days | 7 days | M
Purchase and ship tablet | Purchase of tablet. Shipping will be delayed by 3-4 days. | 11 | 4 days | 7 days | 11 days | M
Milestone 3: Installation of Tablets
Update POS System to be compatible |  | 3 | 1 day | 2 days | 5 days | L
Schedule electrician | To take 2 half days for each | 4 | 2 days | 4 days | 6 days | M
Install tablets | Upgraded devices shipment ddelayed | 1 | half day | 1 day | 5 days | M
Test the newly installed tablets and POS System | Note any ones needing change | 1 | 1 day | 1 day | 2 days | M
Document necessary information about installation | For guidance and future reference | 1 | 1 day | 1 day | 2 days | M
Prepare a plan for maintenance, repairs & updates. |  | 2 | 1 day | 2 days | 4 days | M
Milestone 4: Configurations of Tablet and POS System | Consider additional features
Enable GPS location services and tracking on each tablet | For security and tracking purposes | 4 | 2 days | 4 days | 6 days | L
Finalize menu & coupon value designs | Awaiting Carter's final draft | 10 | 7 days | 9 days | 12 days | M
Upload menu and coupon values |  | 1 | 1 day | 2 days | 3 days | M
Milestone 5: Training Preparation
Plan training program for employees | to train them on usage | 2 | 1 day | 2 days | 4 days | M
Create a procedure for securing tablets at end of night | to avoid thefts | (4 hours) | 2 hours | 4 hours | 6 hours | H
Include payment security talking points in training | To lessen the worry of customers | (2 hours) | 1 hour | 2 hours | 3 hours | H
Include information about payment portal security in training |  | (2 hours) | 30 minutes | 1 hour | 2 hours | H
Document any changes to waitstaff pay and tips |  | (2 hours) | 30 minutes | 1 hour | 2 hours | M
Milestone 6: Training Program for Employees
Conduct meeting to enlighten staff on the training | Introduce the ideas to the staff for staff buy-in | 1 hour | 30 minutes | 45 minutes | 1 hour | M
Train General Managers on new software | Seydou and Peta conduct this. So they can train their staffs | 5 hours | 2 hours | 4 hours | 6 hours | M
Schedule training with all employees | Trained General Managers conduct this training | 3 hours | 1 hour | 2 hours | 3 hours | M
Schedule a Sunday test run involving family & friends | To test the efficency and correct mistakes | 1 | 6 hours | 12 hours | 1 day | M
Milestone 6: New-Hire Process
Conduct staff meeting to determine need for any additional hire
Assess payroll and staff requirements
Create a plan to hire for necessary roles
Milestone 7: Additional Tasks
Compile list of menu items available for coupon selection
Research and contact third-party ordering services

## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration (Days) | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone 1: Preparation for Tablet Integration | Meetings, Processes & research
Conduct staff meetings to prepare for tablet integration | Workflow, strategies, features, concerns, recommendations |  |  | 1
Brainstorm on various ways to track project effeciency |  |  |  | 1
Develop a process to record and analyze new metrics |  |  |  | 1.5
Research different tablets and their features |  |  |  | 4
Research 2 to 3 vendors |  |  |  | 3
Milestone 2: Purchasing of Tablets
Generate quotes and review costs |  |  |  | 5
Test out different tablets | Review options |  |  | 3
Choose a suitable tablet |  |  |  | 1
Create contracts, purchase orders, and statements of work for vendors |  |  |  | 5
Purchase and ship tablets | Purchase of tablet. Shipping will be delayed by 3-4 days. |  |  | 11
Milestone 3: Installation of Tablets
Update POS System to be compatible |  |  |  | 3
Schedule electrician |  |  |  | 4
Install tablets |  |  |  | 1
Test the newly installed tablets and POS System |  |  |  | 1
Document necessary information about installation |  |  |  | 1
Milestone 4: Configurations of Tablet and POS System
Enable GPS location services and tracking on each tablet |  |  |  | 4
Finalize menu & coupon value designs |  |  |  | 10
Upload menu and coupon values |  |  |  | 1
Milestone 5: Training Preparation
Plan training program for employees |  |  |  | 2
Create a procedure for securing tablets at end of night |  |  |  | (4 hours)
Include payment security talking points in training |  |  |  | (2 hours)
Include information about payment portal security in training |  |  |  | (2 hours)
Document any changes to waitstaff pay and tips |  |  |  | (2 hours)
Milestone 6: Training Program for Employees
Conduct meeting to enlighten staff on the training | Introduce the ideas to the staff for staff buy-in |  |  | 1 hour
Train General Managers on new software | Seydou and Peta conduct this. So they can train their staffs |  |  | 5 hours
Schedule training with all employees |  |  |  | 3 hours
Schedule a Sunday test run involving family & friends |  |  |  | 1
Milestone 6: New-Hire Process
Conduct staff meeting to determine need for any additional hire
Assess payroll and staff requirements
Create a plan to hire for necessary roles
Milestone 7: Additional Tasks
Compile list of menu items available for coupon selection
Research and contact third-party ordering services

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Tabletop tech speeds up service and boosts profits, study says | https://www.restaurantdive.com/news/tabletop-tech-speeds-up-service-and-boosts-profits-study-says/560152/ | 20-05-2022 | Identified tasks on data leaks and cyber risks
How does a Digital Menu App Add Value to your Restaurant Business? | https://www.restroapp.com/blog/digital-menu-app-restaurant-business/ | 20-05-2022 | Identified tasks on sending notifications to customers once the food is ready and being sent to the table. and displaying dishes nutritional values in the tablet

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer satisfaction | Average ticket time - 8 min for appetizers and 12-15 minutes for entrees | What are the advantages of reducing of average ticket time | old average ticket time and current average ticket time | FALSE
| 1 min payment check out time | What are unintended outcomes of one minute pay check time | Verify customer reviews, track customer care queries on payment gateway | FALSE
| Less than 5% of customers to report technical issues with tablets | How can we improve the technical support | Following incidents SLA's | FALSE
| Having 98% order accurately placed | How many percentage of wrong orders? | Orders returned after payment | FALSE
| Decrease customer wait time to 10 minutes or less before seated | How are customer's feelings for very less wait time before seated | Customer surveys at the end | FALSE
| Increase customer retention in tablet areas by 5% | How to improve customer retention | Painpoints in customer reviews and surveys | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Average ticket time - 8 min for appetizers and 12-15 minutes for entrees | What are the advantages of reducing of average ticket time | old average ticket time and current average ticket time | How much time did you wait before your order arrived after placing an order | Open-ended | Open-ended
|  |  | what would you rate our order readiness | Multiple choice | Very Slow | Slow | Can be quicker | Fast | Very Fast
1 min payment check out time | What are unintended outcomes of one minute pay check time | Verify customer reviews, track customer care queries on payment gateway | Is our one min quick payment option working with your card | Yes/No | Yes | No
|  |  | On a scale of 1-5, how efficient is our quick payment checkout? | Scaled | Very Satisfied | Somewhat satisfied | Neither satisfied nor dissatisfied | Somewhat dissatisfied | Very dissatisfied
Less than 5% of customers to report technical issues with tablets | How can we improve the technical support | Following incidents SLA's | Did you face any technical issues with our tablets | Yes/No | Yes | No
|  |  | We believe, our technical staff would have resolved the issue any technical issues within no time. Did they? | True/False | TRUE | FALSE
Having 98% order accurately placed | How many percentage of wrong orders? | Orders returned after payment | Did you face any misordering? | Yes/No | Yes | No
Decrease customer wait time to 10 minutes or less before seated | How are customer's feelings for very less wait time before seated | Customer surveys at the end | How much time did you wait before table is allocated to you? | Open-ended | open-ended
|  |  | Did your wait time less time than the last time you visited? | Multiple choice | Never visited before | Slightly reduced | Reduced noticably | Increased
Increase customer retention in tablet areas by 5% | How to improve customer retention | Painpoints in customer reviews and surveys | On an average how many times did you visited our restaurant in a month? | Open-ended | open-ended