## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Project team | Went well | Tablets installation and working went well in downtown and north locations | 30-40% of people voted they had great experience with tablets
Project team | Needs improvement | Didn't see expected decrease in table turn time | 54% of people had waited for more then 15mins before table is allocated | Decrease ticket time effectively to reduce wait time
Project team | Went well | Easy to keep track of tickets | Smooth flow of tickets and priorities
Project team | Needs improvement | Food orders were sent back due to any reason of wrong order/ bad delivery which leads to food waste | 28% of orders were sent back due to the Wrong entree being brought out, - Didn’t leave off the parsley - Entree was overcooked - I asked for a side of fries and got mashed potatoes and more | Head of cheif must verify the orders before sending orders out
Project team | Needs improvement | Technical maintenance issues that just comes with the territory | Only 12% of customers reported technical issues with tablets | Update the process manual so that the solution is easy to find next time that issue comes up
Project team | Needs improvement | Participants for birthday club | Only 16% of customers signed up for it | Updating the content in website and on tablets to make program more clear
Project team | Needs improvement | Unplanned internal operation issues | Effected smooth implentation of tasks | Understand locations history before planning gets underway
Project team | Needs improvement | Waitstaff training process | Lack of understand b/w front of house and back of house tasks split | Develop a more comprehensive training session, or even break the training up into two parts
Customers | Customers | Please give us the option in the future of choosing a waiter | Request from a customer | Could analyze more of how it works effectivey